## Arkusz1
Descryption | Evaluation | Likehood | Impact Level | Responsibility | Response | Control Measures
Power Cut | Lossing local unsaved work | Low | High | Local Energy Provider | Waiting untill power is back/going to work to some cafetery with Wi-Fi | Save and push my code frequently
Github Servers Go Down | I would be unable to push my code to my repo | Very ulikely | Medium | Github servers | Working on saved files | Push my code frequently and store repo localy
Possibility of sickness | I would be less focused/unable to work, dependent on sickness | Low | Low-HIgh | Me | Rest, treat my sicknes. Work only if possible. | Dont overwork, look after myself
Computer/System issues | I wouldnt be able to work correctly/at all | Low-Medium | Medium-High | Me | Solving the issues/working on apps that have no issues | Update my PC and apps whenever there is an update
Internet Connection issues | I would be able to work localy, but unable to push my code to repo | Low | Low | Internet provider | Waiting untill connection is back/going to work to some cafetery with Wi-Fi | Save and push my code frequently